## Dk stone
Test Case_no | Module->Sub module | Issue details | Test Data | Bug Screenshot | Final Status | Dev Status | QA Status
Web issues
TC_001 | Admin->Stone->Customer | Customer create korte gele showing error |  | Screen shot | Passed
TC_002 | Admin->Stone->Customer | Web & apk field name mismatch. Company name (Apk), Customer Name(Web) |  |  | Observation | If client want, then given
TC_003 | Admin->Stone->Customer | Customer creation a 6 ta image upload er option ase, front page a only 2 ta show hoi |  | Screen shot | Observation | If client want to show 6, then given
TC_004 | Admin->Stone->Customer | After click "View" button, then clieck "Cancel" button, page auto redirect to 'Asphalt' menu |  | Screen shot | Passed
TC_005 | Admin->Stone | Stone a ghat name ashtese "dk coal" theke. stone a ghat name er kono option thakbe na |  | Screen shot | Passed
TC_006 | Admin->Stone | Complain & TA/DA both menu showing same 404 error status |  |  | Passed
TC_007 | Admin->Stone->Payments | Apk theke "Account Number" field a data dile, web a "Branch name" show kore |  | Screen shot | Passed
TC_008 | Admin->Stone->Sales order (stone)->Delivery point | "Transport Type, Transport No." field's data missing. Also "zone" spelling mistake |  | Screen shot | Passed
TC_009 | Admin->Stone->Sales order (stone)->Delivery point | "Sales Order ID" showing wrong |  | Screen shot | Passed
TC_010 | Admin->Stone->Sales order (stone)->Mobile sales order | Akta case payment & delivery korar por "Business Unit Head" tab theke invisible hoye jacse | SS for Oracle ID | Screen shot | Passed
TC_011 | Admin->Stone->Sales order (stone)->Mobile sales order | In new tab, "Transport Type" showing wrong data |  | Screen shot | Passed
TC_012 | Admin->Stone->Sales order (stone)->Mobile sales order | "Edit" kaaj kore na |  | Screen shot | Passed | order rate edit kora jabena
TC_013 | Admin->Stone->Sales order (stone)->Mobile sales order | "Order Type" always showing "Credit" & "Do ID". Cash diye order korleo Credit show kore |  | Screen shot | Passed | Cash & Credit always "Do id" generate hobe | Business Unit head approve korle Do ID generate hobe
TC_014 | Admin->Stone->TA/DA | Approve korar por "Reject" kora jacse na ar |  | Screen shot | Passed
TC_015 | Admin->Stone | TA/DA & Attendance a "Finance Approve" er jaigai "Accounts Approve" hobe |  |  | Passed
TC_016 | Admin->Stone->Sales order (stone)->Mobile sales order | "View" button a click korle upore ribbon a "Edit" likha show kore |  | Screen shot | Passed
TC_017 | Admin->Stone->Sales order (stone)->Delivery point | "Edit" kaaj kore na |  | Screen shot | Passed
TC_018 | Admin->Stone->Sales order (stone)->Delivery point | In 'Delivery point' tab, "Order Amount" & "Sales Manager" column a data pore na |  | Screen shot | Pending | without sales manager | Need to discuss with client for clarification
TC_019 | Admin->Stone->Sales order (stone)->Delivery point | "Final delivery" tab a edit kaj kore na |  | Screen shot | Passed | final delivery te edit thakbena
TC_020 | Admin->Stone->HO employee | Edit korte gele "Zone & Area" wrong show kore dropdown a |  | Screen shot | Passed
TC_021 | Admin->Stone->Sales order (stone)->Delivery point | "Date Range" filter kaaj kore na |  |  | Passed
TC_022 | Admin->Stone->Attendance | Attendance module er "Attendance Reason" column er data thik nai |  |  | Failed
Apk issues
TC_001 | Sales Officer->Order | When do "edit", then page become blank & sometimes it redirect to back page |  | Screen shot | Passed
TC_002 | Sales Officer->Order | Last order kora data, next order ao show hocse |  | Screen shot | Passed
TC_003 | Sales Officer->Order | Deactivate SKU gulo order korar time pawa jacse |  | Screen shot | Passed | need arin bhai's help |  | mobile_api/api/Corporate_Sales_order/getSkuNameStone
TC_004 | Sales Officer->Existing Customer | Web a ''Oracle ID' dewar kono field nai. Apk te show korse "0". Need to remove from 'apk' or add in 'web' |  | Screen shot | Passed | Client wanted, that's why given |  | http://shahcem.babl.xyz/mobile_api/api/Corporate_Sales_order/getCustomerDataDC bhai ei api te oracle id =0 astece. [{ "name":"emp_id","value":"18"}, {"name":"role_id","value":"129"}, {"name":"manager_id","value":"0"}, {"name":"ghat_id","value":"0"}, {"name":"data_type","value":"stone" }]
TC_005 | Sales Officer->New Customer | Drop down data should be "BEFTN" |  | Screen shot | Passed
TC_006 | Sales Officer->Complain | 'Delivery Date' field er "ok & cancel" button khali chokhe dekha jacse na |  | Screen shot | Passed
TC_007 | Sales Officer->TA/DA | TA te drop-down a "Bike" missing. Web a bike = 'Yes' dewa ase |  | Screen shot web | Passed | maruf vai dependancy |  | http://120.50.42.151/mobile_api/api/Login/login need to add bike_status in the following api.
TC_008 | Sales Officer->Attendance | Present dileo web a "Absent" e porse |  |  | Passed | "" |  | [id=1, data_type=stone, column_id=1743064321450, emp_id=18, attendence_status=1, present_location=1, absent_reason=-1, lat=24.5407447, lon=92.0560614, distance=0, leave_type_id=0, remarks=test, first_date=, last_date=, is_synced=0] http://shahcem.babl.xyz/mobile_api/api/Corporate_Sales_order/insertAttendenceDC
TC_009 | Sales Officer->Attendance | Apk te "Leave" option thakte hobe |  | Screen shot | Dev DOne
TC_010 | Sales Officer->Report | Order, delivery, payment korar poreo, "Report" module a kono data show hocse na |  |  | Passed
TC_011 | Sales Officer->Order | Order details and Order Summary sometime exchanged. (St = summary, dk cl = details) |  |  | Passed | please recheck properly. This is dangerous issue.

## Polar Image
Test Case_no | Module->Sub module | Issue details | Bug Screenshot | Final Status | Dev Status | QA Status
APK issues
TC_001 | Today's route (order and no order), Today's outlet list, Outlet verify, PDF Requisition, Complain (Secondary report->Fridge complain report), CSR (collection) | Camera use kore image dile nicse na |  | Passed |  | **mdr22582 **dbo22545 **csr16864 **tm8226 Pass= p2345
TC_002 | Today's route (order and no order), Today's outlet list, Outlet verify, PDF Requisition , Complain (Secondary) | Image dewar time "Gallery" option need to remove |  | Passed
TC_003 | csr16864->All module | CSR role er je kono module a click korlei upore "1" show hocse | Screen shot | Passed |  | issue fixed after clear data
TC_004 | csr16864->Collection | Image newa jacse na. Camera option isn't clickable (Version 13 & 14) | Screen shot | Passed
TC_005 | tm8226->PDF verify->Verification | Image function isn't working |  | Passed
TC_006 | tm8226->PDF verify->Installation | Image function isn't working |  | Passed
TC_007 | tm8226->PDF verify->Audit Process | After click, auto redirect to previous page |  | Passed
Web issues
TC_001 | Polar->Primary promotion | After click "Edit" button, edit hoi na (Value theke quantity korte gele) | Screen shot | Pending |  | Test server issue. Okay in Live server
TC_002 | dbo22545->Secondary report->এম ডি আর এর দোকান ভিজিট রিপোর্ট | Image isn't open | Screen Shot | Passed
TC_003 | Mis super->Complain (Secondary report->Fridge complain report) | image isn't visible in web | Screen shot | Passed
TC_004 | Mis super->Master->Outlet->View Outlets | Web theke create kora data, image upload korar poreo "Image not found" show kore | Screen shot | Failed | Sajjad vai | Test server issue. Okay in Live server
TC_005 | mdr22582->PDF Requisition | Apk theke image dile, Web a image dekha jai na (Apk 13 version) | Screen shot | Passed

## Dk coal
Test Case_no | Module->Sub module | Issue details | Bug Screenshot | Final Status | Dev Status | QA Status
APK issues
TC_001 | Order->Order summary | Image direct camera theke dile nicse na | Screen shot | Passed
TC_002 | Order->Order details | Approve er agey "Advance ref ID" pabe na | Screen shot | Passed
TC_003 | Sales officer->Payment | Sales officer diye login korle Customer pawa jacse na | Screen shot | Passed
TC_004 | Admin/Accounts->Dk coal->Customer | When the customer is created from the APK, the data directly goes to the "Approved" tab instead of appearing in the "New" tab | Screen shot | Passed
TC_005 | Ghat Incharge->Payment | Payment a new created customer pawa jacse na |  | Passed
TC_006 | Sales officer->Order | When do "Edit", then it redirect to back screen | Screen shot | Passed
Web issues
TC_001 | Order->Order details | Apk theke order korle web a all ghat name pawa uchit. Kintu akhn just nijr ghat e show korse | Screen shot | Passed
TC_002 | Dhaka coal->Advance payments | Apk theke Image upload korle web a porse na | Screen shot | Passed
TC_003 | Dhaka coal->Report dc | Data pawa jai ni. "Delivery Summary Customer Wise Report" ¦¦ "Delivery Summary Ghat Wise Report" |  | Passed

## Shah RMC TADA Issue
Test Case_no | Module->Sub module | Issue details | Bug Screenshot | Final Status | Dev Status | QA Status | Test Data
APK issues
TC_001 | TA/DA->Travel Allowance->Click + icon | First select "Bike" then on the same page "TA Type" field's drop-down select by another data (CNG, Petrol etc). In this scenario, there didn't found "Amount" field | Screen shot | Passed |  |  | bike
TC_002 | TA/DA->User profile | "Dealer" option need to remove | Screen shot | Passed |  |  | APK user 90
TC_003 | TA/DA-> + icon | User can entry amount with a zero at the beginning of the "Amount" field. This needs to be restricted | Screen shot | Passed
TC_004 | Login-> Area Manager | Column need to add in apk "Expense"->Courier, Night Casting | Screen shot | Passed
TC_005 | Login-> Area Manager->RMC->RMC ta/da | Jodi apk theke duita request kori same data (CNG) diye & alada amount (10 & 20) tahole web a last amount show kore only. APK theke validation diye atkanu dorkar | Screen shot | Passed
TC_006 | Login-> APK user | Expense->Expense Type= "Select" diye data dewa jacse | Screen shot | Passed
TC_007 | Login-> APK user | APK theke "Expense->Hotel->Rest of the country" select kore expense submit korle Web a data pore na kono | Screen shot | Passed
Web issues
TC_001 | RMC->RMC ta/da | Image isn't visible in web | Screen shot | Failed | Server issue |  | TA
TC_002 | RMC->RMC Employee->Click 'Search'->Click 'Edit' | When do edit, then "Designation" field's data found removed & "Zone Name", "Area Name" field found auto selected data by default | Screen shot | Passed |  |  | TA->HR 1
TC_003 | RMC->RMC ta/da | "Image" & "Map" tab isn't visible in web |  | Passed |  |  | TA
TC_004 | RMC->RMC ta/da | Jodi apk theke duita request kori "parking" diye & alada amount, tahole web a last amount show kore only. Comma diye duitai show kora dorkar | Screen shot | Passed |  |  | Expense, APK user 90
TC_005 | Login-> Area Manager | SL no. found mis-sequence | Screen shot | Passed |  |  | Mina area manager 90
TC_006 | Login-> Finance | Finance tab a data newar por "Edit" button er kono kaaj thaka uchit na. Need to delete this button from there | Screen shot | Passed
TC_007 | Login-> Area Manager | APK te 'DA'->"Night Hold" diye data dile sheita web er 'Expense'->"Night Hold" column a porse. Need to add that column in 'DA' portion & remove from expense | Screen shot | Passed
TC_008 | RMC->RMC ta/da->Select 'Area & Officer'->Click 'Search' | For "TA Status" portion, "Octane" field's name should be "Petrol", according to APK | Screen shot | Passed |  |  | TA->Mirzapur, APK user 27
TC_009 | RMC->RMC Employee->Click 'Search'->Click 'Edit' | When do edit, then "Manager" field's data found auto selected (Akbor hossain) | Screen shot | Passed |  |  | test 90
TC_010 | Login-> Area Manager->RMC->RMC ta/da | Expense->'Courier' a data dile 'Night Casting' a porse & 'Night Casting' a data dile 'Courier' a porse | Screen shot | Passed
TC_011 | Login-> Area Manager->RMC->RMC ta/da | DA te 'Maintenance' thakbe na. Expense->Maintenance diye data submit korle web a DA & Expense dui column ei data porse | Screen shot | Passed

## Bridge test issue
Test Case_no | Module->Sub module | Issue details | Test Data | Bug Screenshot | Final Status | Dev Status | QA Status
TC_01 | Master Data->Geo Master | When do edit, data missing from "Description" field & showing "0" | Rangpur territory 2 | Screen shot | Passed
TC_02 | Master Data->Gifts Index | Gift index' theke "Edit or Create" er time cancel button a click korle direct "Geo Hierarchy list" a niye jacse |  | Screen shot | Passed
TC_03 | Master Data->Doctor Index | Doctor index' theke "Create" er time cancel button a click korle direct "Chemist index" a niye jacse |  | Screen shot | Passed
TC_04 | DO->Sales order->primary order->Depot Order | "Order Create"->"SL no." column showing sequence mismatch after delete data |  | Screen shot | Passed
TC_05 | DO->Sales order->primary order->Depot Order | "Edit"->Akta data akbar decrease korle ar increase kora jai na | Nouga Depot 7 | Screen shot | Passed | Screen shot 1 | Screen shot 2
TC_06 | DO->Payments->Payments index | After search, double data showed |  | Screen shot | Passed
TC_07 | Super admin->Entertainment expense | After click "View" button, then "Show image" button is turn invisible |  | Screen shot | Passed
TC_08 | Super admin->Entertainment expense | After click "Show image" button, then image isn't visible & download as well |  | Screen shot | Passed
TC_09 | Super admin->Entertainment expense | Apk theke "Edit" korte gele image remove hoye jai |  |  | Passed
TC_10 | Super admin->Travel expense | Apk theke "Edit" korte gele image remove hoye jai |  | Screen shot | Passed
TC_11 | Super admin->Travel expense | "Transport Type" always rickshaw show kore |  | Screen shot | Passed
TC_12 | Chemist Visit & Doctor Visit & Employee Feedback | Functionality isn't working |  |  | Passed
TC_13 | Master Data-> Chemist index-> verified tab | Action not working properly on this tab. |  |  | Passed
TC_14 | Secondary sales order ->Edit | Sku edit ->duplicate sku & sl mismatch after delete |  |  | Passed
TC_15 | Secondary sales order ->Edit | Je product er stock nai seta zero kore update kore approve kora jabe |  |  | Passed | hobena
TC_16 | Admin->Factory stock->Stock index | "Enter PIN" button isn't functioning |  | Screen shot | Passed
TC_17 | DO->Master Data-> Chemist index | Image isn't visible in web |  | Screen shot | Passed
TC_18 | Master Data->Employee list->Edit | When do edit, image isn't found. Also "Full view & Download" button isn't working |  | Screen shot | Passed
TC_19 | Master Data-> Chemist index | Image upload er option kothai? |  | Screen shot | Passed
TC_20 | DO->Sales order->primary order->Depot Order | Edit korte gele "Amount" field er fraction er porer digit count hocse 405310, kintu filter korar por fraction shoho table a visible hoi 405,309.79 |  | Screen shot | Passed | Screen shot 2
TC_21 | DO->Master Data-> Chemist index | "Show image" button a click korar por "View" button a click korle wrong pop-up page open hocse |  | Screen shot | Passed
TC_22 | DO->Payments->Payments index | APK theke "payment" korar por "Receive Amount" field a kono data pore na |  | Screen shot | Passed
TC_23 | DSM->Sales order->Primary Order | When do edit, Amount shows mismatch |  | Screen shot 1 | Passed | Screen shot 2
Report issues
TC_23 | Reports-> Monthly Product Wise Sales Rsm | Drop-down a only region ashbe. akhn area, territory sob show kore | Faridpur region | Screen shot | Passed
TC_24 | Reports-> Monthly Product Wise Sales FM | Drop-down a only region ashbe. akhn area, territory sob show kore |  |  | Passed
APK issues
TC_01 | MO->Verify chemist | "Chemist Address" field isn't showing proper & full data |  | Screen shot | Passed
TC_02 | MO->Order->"+" | Search data isn't visible properly |  |  | Passed
TC_03 | Profile | Name er majhe space thaka uchit |  | Screen shot | Passed
Apk issues 4th march
TC_01 | MO apk->Payment¦¦DO web->Sales order->Secondary order->Delivery complete Tab | Apk theke payment korte gele "Amount & Due" vul show kore | Screen shot apk | Screen shot web | Passed
TC_02 | MO apk->Payment | Web theke delivery korar agey apk te "Invoice no" show korbe na |  | Screen shot apk | Passed
Web issues
TC_01 | Promotion/Bonus->Bonus index | Edit korle shei product er jonno bonus kaaj kore na |  | Screen shot | Failed
TC_02 | Report->Monthly dues report, sales and collection report | "Invoice Amount" field showing wrong value | Total 1500, after discount net payable 1425, 1000 given in apk, due 425 in apk | Screen shot | Passed

## Bridge Live issue
Test Case_no | Module->Sub module | Issue details | Bug Screenshot | Final Status | Dev Status | Priority
TC_01 | Master Data->Farm->Create | After click on "Cancel" button, then page re-direct to 'Doctor Index' | Screen shot | Passed |  | High
TC_02 | Master Data->Employee list | "In-active" button ei khane kono kaj korse na. Need to remove | Screen shot | Passed |  | High
TC_03 | Master Data->Employee list->Edit | When do edit, image isn't found. Also "Full view & Download" button isn't working | Screen shot | Passed |  | High
TC_04 | Master Data->Chemist Index | Image upload er kono option nai, but "Chemist image" nam er field rakha hoyese web a | Screen shot | Passed |  | High
TC_05 | Master Data->Chemist Index | After click on image show , edit button showing image |  | Passed |  | High
TC_06 | Master Data->Products->Dosage form | Detail dekhte gele upore "Edit" show kore. It should be "Detail/View" | Screen shot | Passed |  | Medium
TC_07 | Master Data->Products->Product category | Detail dekhte gele upore "Edit" show kore. It should be "Detail/View" |  | Passed |  | Medium
TC_08 | Master Data->Products->Product category | "Edit" button a click kore 'Description' ditey gele save korar por '0' show kore | Screen shot | Passed |  | High
TC_09 | Master Data->Products->Product volume | "view" button a click korle upore "Edit" show kore. It should be "View" |  | Passed |  | Medium
TC_10 | Master Data->Products->Product unit | "Create" korar shomoy "Product Unit Code" nam er kono field silo na. Edit & View korle ei field show kore. Need to remove | Screen shot | Passed |  | High
TC_11 | Master Data->Products->Product unit | "view" button a click korle upore "Edit" show kore. It should be "View" |  | Passed |  | Medium
TC_12 | Master Data->Products->Product Unit's Mapping | "view" button a click korle upore "Create" show kore. It should be "View" |  | Passed |  | Medium
TC_13 | Master Data->Products->Product Master | After search, Edit & View korle page blank hoye jai | Screen shot | Passed |  | High
TC_14 | Master Data->Farm->Create | Drop-down a MO ashe na, all MO pabe | Screen shot | Passed |  | High
TC_15 | Factory stock->Stock index | "Enter PIN" button kono kaj kore na. Below "Update stock" button kono kaj kore na | Screen shot | Passed |  | High
TC_16 | Admin->Target | Target akta reject korar por arekta target create korle, ager rejected target remove hoye jai. Rejected target theke jawa uchit | Screen shot | Passed |  | High
TC_17 | DO->Promotion/Bonus | Date expired bonus gulo akhno pawa jacse order korle, Need to fix this | Screen shot | Passed |  | High
TC_18 | DO->Master Data-> Chemist index | Deactive korar kono option nai, Need "Deactive" button | Screen shot | Passed |  | High
TC_19 | DO->Sample Distribution | Save' korle page blank hoye jai | Screen shot | Passed |  | High
TC_20 | Admin->Promotion/Bonus | "Edit" button a click korle upore "Add" show kore. It should be "Edit"¦¦ Also "View" button a click korle upore "Add" show kore. It should be "View". | Screen shot | Passed |  | Medium
TC_21 | Admin/DO->Employee Feedback | "Edit" button hobe na. It should be "View" | Screen shot | Passed |  | Medium
TC_22 | DO->Master Data->Farm | Ribbon name showing wrong | Screen shot | Passed |  | Medium
TC_23 | Admin/DO->Doctor/Chemist/Farm visit | Apk theke data submit korle web a data pore na | Screen shot | Passed |  | High
TC_24 | Admin/DO->Employee Feedback | Apk theke data submit korle web a data pore na | Screen shot | Passed |  | High
TC_25 | Do->Market return->Marketreturn index | "Create return" korle 'generate' button a click korle save hocse kina bujha jai na. Pore serach korle jotobar click kora hoise, toto data dekha jai | Screen shot | Passed |  | High
TC_26 | Report->Monthly dues report | Fraction (দশমিক) er por two digit hobe | Screen shot | Passed |  | High
TC_27 | Report->Sales & collection report | "Cheque no" field er nam hobe "Account number"¦¦Grand total need to remove¦¦zero er pore minus (-0) uthe jabe | Screen shot | Passed |  | High
TC_28 | Report->GEO report->Live tracking report (ASM) | Role name capital hobe |  | Passed |  | Medium
TC_29 | Report->GEO report->Live tracking report (FM) | Role name capital hobe¦¦Search kaj kore na¦¦Field name should be "FM" | Screen shot | Passed |  | High
TC_30 | Report->GEO report->Live tracking report (RSM) | Location showing wrong. Dhaka theke login korar pore sylhet show kore | Screen shot | Passed |  | High
TC_31 | Master Data->Chemist Index | Image upload er option ase, but Image dekha jai na | Screen shot | Passed |  | High
TC_32 | Master Data->Products->Product category | Create korar por 'Description' '0' show kore¦¦Field name found mismatch | Screen shot | Passed |  | High
TC_33 | Admin->Target | Target akta approve korar por arekta target create korle, ager "Approved" target remove hoye jai. Approve target theke jawa uchit | Screen shot | Passed |  | High
TC_34 | Master Data->Products->Product category | Edit korte gele "Code" field a 'Name' field er data show korse | Screen shot | Passed |  | High
TC_35 | Admin/DO->Doctor visit | "Remarks" field apk te nei. SO ei field a data dewar option nei. Need to remove. | Screen shot | Passed | Said shimul vai | High
TC_36 | Admin/DO->Farm visit | Farm er visit index ta left menu te ditey hobe |  | Passed |  | High
TC_37 | Full system | Shob jaigai Employee (HO, FM, ASM, RSM etc.) capital a dekhate hobe |  | Passed |  | Medium
TC_38 | Report | Rsm & Fm should be capital | Screen shot | Passed |  | Medium
TC_39 | Admin/DO->Farm visit | Apk te "Purpose" a data dile web a shei data "Population" field a porse && "Purpose" field a 1000 show korse | Screen shot | Passed | Purpose a data pore but "Population" field a 1000 show kore | High
TC_40 | DO->Payments->Payments index | APK theke "payment" korar por "Receive Amount" field a kono data pore na | Screen shot | Passed | Need clarification of Shimul vai | High
TC_41 | Report->Monthly product wise sale RSM & FM | It should be "Filter" | Screen shot | Passed |  | Low
TC_42 | Report->Time Stamp Report | Map isn't showing | Screen shot | Passed |  | High
TC_43 | Report->Time Stamp Report | "Working Hour" showing wrong |  | Passed |  | High
TC_44 | Admin->Master->Depot & Central Index | When do edit & click "Cancel" button, then "404 page not found" error occur | Screen shot | Passed |  | High
TC_45 | DO->Target->Target Upload | "Upload" button isn't working | Screen shot | Passed |  | High
TC_46 | DO->Sample distribution | Jei product diye primary order kora hoyese, only shei gulo pabe. Akhn shob pacse. (1st product select a thik show kore but 2nd product select a wrong show kore) | Screen shot | Passed |  | High
TC_47 | Admin->Employee feedback | "Feedback" field need to remove. User "View" theke feedback dekhbe | Screen shot | Passed |  | Low
TC_48 | DO->Sales Order->Secondary order->Order Index->Delivery Tab | After click "Create loading sheet", then 'Net payable' a bonus product er amount o add hoye show kore. Bonus amount zero hobe | Screen shot | Passed |  | High
TC_49 | Admin/DO->Doctor/Chemist visit | "Type = General visit" hoile Purpose a data "1" show kore always | Screen shot | Passed |  | High
TC_50 | Master Data->Download Excel | Excel download korle Action er column gulo show kore. Need to remove | Screen shot | Failed | If user want, then given | Low
TC_51 | Admin->Travel/Entertainment | Image dekha jai na | Screen shot | Pending | New Development needed | Medium
TC_52 | Admin->Entertainment Expense | Tab name showing wrong. It should be "Entertainment Expense" | Screen shot | Pending | New Development needed | Medium
TC_53 | DO->Master Data-> Chemist index | APK theke image dileo web a "Image Not Found" show kore | Screen shot | Pending |  | High
TC_54 | Admin->Attendance->Attendance Index | Accept/Reject option need to remove | Screen shot | Requirement |  | High
TC_55 | Admin->Travel/Entertainment | Image dekha jai na | Screen shot | Requirement |  | Medium
TC_56 | Admin->Entertainment Expense | Tab name showing wrong. It should be "Entertainment Expense" | Screen shot | Requirement |  | Medium
TC_57 | Admin->Travel/Entertainment | Full module will be changed according to client end |  | Requirement |  | High
APK issues
TC_01 | Order | Edit' korte gele "ADD" button color korte hobe, (Now it look like disable button) | Screen shot | Passed |  | Low
TC_02 | Order | দশমিকের পরে ২ digit hobe | Screen shot | Passed |  | Medium
TC_03 | Profile | Name er majhe space thaka uchit | Screen shot | Passed |  | Medium
TC_04 | Order | দশমিকের পরে ২ digit porjonto show kora uchit front page a | Screen shot | Passed |  | Medium
TC_05 | MO->Order->No order | Need to remove from apk |  | Pending | Clint Clearification Needed | High
TC_06 | Report->GEO report->Live tracking report (RSM) | Akbar login korle 4/5 bar database a login data portese & live location ao multiple indicate kortese web a. apk dependency | Screen shot | Passed | (polash vai) | High
TC_07 | DO->Master Data-> Chemist index¦¦Admin->Doctor visit->Index¦¦ | APK theke image dileo web a "Image Not Found" show kore | Screen shot | Passed | (polash vai) | High
TC_08 | Admin/DO->Chemist visit | Apk te "Type = General visit" hoile web er 'Purpose' field a data "1" show kore always | Screen shot | Passed | api task (polash vai) | High
TC_09 | MO->Order | "Order type"= Cash hoile, order kora jai na | Screen shot | Passed |  | High

## WEB
Test Case_no | Module->Sub module | Issue details | Bug Screenshot | Final Status | Dev Status | QA Status | hi
TC_001 | Master Data->Geo Hierarchy List | When download excel, then "Delete->>>" word visible. Need to remove | Screen shot | Passed | Done
TC_002 | Master Data->Geo Hierarchy List | Breadcrum mismatch. It should be "Master Data->Geographical Hierarchy" | Screen shot | Passed | Skip
TC_003 | Master Data->Geo Master | When download excel, then "Delete->>>, Details->>>" word visible. Need to remove | Screen shot | Passed | Done
TC_004 | Master Data->DEPOT & Central store->Type Index | Menu name mismatch. It should be "View" | Screen shot | QA observation | Done
TC_005 | Master Data->DEPOT & Central store->Type Index | When click, "DOP index" for move backward, then page showing "404 not found" error | Screen shot | QA observation | Done
TC_006 | Master Data->DEPOT & Central store->DEPOT & central index | Menu name mismatch issue | Screen shot | QA observation | Done
TC_007 | Master Data->Chemist Index | "Select Thana" field need to remove | Screen shot | Passed | Done
TC_008 | Master Data->Products->Product type | When edit something then below button name should be "Update" | Screen shot | Passed | Done
TC_009 | Master Data->Products->Dosage Form | When click on "Detail" button, then Breadcrum name should be "Master Data->Products->Dosage Form" | Screen shot | QA observation | Skip
TC_010 | Master Data->Products->Product Category | When click on "Detail" button, then Breadcrum name should be "Master Data->Products->Product Category" | Screen shot | QA observation | Skip
TC_011 | Master Data->Products->Product Volume | When click on "Edit & View" button, then Breadcrum name should be proper | Screen shot | QA observation | Skip
TC_012 | Master Data->Products->Product Units | Menu name should be "Product Units" | Screen shot | Passed | Done
TC_013 | Master Data->Products->Product Units | When click on "View" button, then Breadcrum name should be proper | Screen shot | QA observation | Skip
TC_014 | Master Data->Products->Product Unit's Mapping | Button name didn't start with "SKU" | Screen shot | Passed | Done
TC_015 | Master Data->Products->Product Unit's Mapping | When click on "Edit" button, then Breadcrum name should be proper |  | QA observation | Skip
TC_016 | Master Data->Products->Product Master | When click on "Edit" button, then Breadcrum name should be proper | , | QA observation | Skip
TC_017 | Master Data->Gifts Index | When click on "Edit" button, then Breadcrum name should be proper |  | QA observation | Skip
TC_018 | Master data> Chemist index | chemsit image and action view pop up need to correction. |  | Issue | Done
TC_019 | sales order> secondary sales order | order can not be approved and delivery if it has no stock |  | Passed | Done
TC_020 | sales order> secondary sales order | Net amount column calculation showing wrong (so id: 1730002280527-725766) |  | Passed | Done
TC_021 | sales order > secondary sales order > create | while order from web, need to rename "factory stock" to "Depot Stock" |  | Issue | Done
TC_022 | sales order > secondary sales order | showing pop up"create loading sheet" if i want to cancel the order from the new tab. need to fix. there is no need to create loading sheet to cancel the order from the new tab and delivery tab |  | Passed | Done
TC_023 | sample distribution> create | depot current stock showing wrong. |  | Issue | Done
TC_024 | Master data> doctore create | code will be uniqe. no can use same code for another doctor |  | Passed | Done
TC_025 | Master data> doctore create | individual depot will get individual MO list |  | Issue | Done
TC_026 | master data > chemist index | if i do blank search, all chemist showing as result. after blank search individual depot will get individual search result |  | Issue | Done
TC_027 | doctor visti | delete "action" column from doctor visit |  | Passed | Done
TC_028 | image | image not showing in the full system |  | Issue
TC_029 | chemist visti | delete "action" column from chemist visit |  | Passed | Done
TC_030 | sales order > edit | Promo details column showing blank |  | Issue |  | API theke promo id lagbe. api te kaj korte hobe.
TC_031 | both market return > create | showing different mo list . need specific mo list specific depot wise |  | Passed | Done
TC_032 | Dashboard | Need to work on dashboard |  | Observation
TC_033 | Market returun> invoice wise | Nothing happens after click on "Generates Return". |  | Passed | Done
TC_034 | Market returun> bulk wise | Nothing happens after click on "Generates Return". |  | Passed | Done
TC_035 | bonus | Need date range filter in this module |  | Issue | Done
TC_036 | market return | jodi offer thake ebong se situation a jodi return hoi tahole offer product se pabe na |  | In Progress | In Progress
TC_037 | manage challan | need to manage invoice in a separate module like polar. where i can get all invoice data wise. |  | Pending
TC_038 | market return> index | view missing for depot officer and view button doesn't work |  | Passed | Done
TC_039 | Market Return> stock | Need to work on return stock added to the main stock automatically . it will be developed in server. |  | Pending | Done
TC_040 | Sales order > delivery tab | Edit should be view and "save , cancel " need to remove |  | Passed | Done
TC_041 | Challan create | bonus prodcut will not be calculate in the challan create page. need to fix. |  | Pending